## Slide 1
VIII. Preparing to execute
Notes: So let’s jump into Phase 2, Preparing to Execute……
Timing: 60 minutes
Flip Charts:
Risk Assessment
Managing the Expectation Gap
Performance Objectives
SMART Objectives
Buy In: ED = RD x CD
Project Team Members

## Slide 2: Checkpoint
-
Client
Relationship
Management
3
4
1
2
Prepare to Execute
Execute the Project
Define
the Need
Review
& Assess
Next:
Prepare to Execute
Ending:
Define the Need
Notes: Checkpoint
Review…..we have not completed the 1st of the stages of the consulting cycle……as a result of that stage, we have a proposal that has been provided to our client…
Preview….what we are about to cover next is the 2nd stage in the consulting cycle, Preparing to Execute, or consider that stage as Planning for the details of the project……
Big view….and that’s important because as we all like to say….”life is in the details”….we typically find that until we get the decision that we have “won” the business we have our work done at a higher level than is often necessary to actually conduct the work…..that’s what we want to complete as a part of this stage……

## Slide 3: The Facilitative Consultant
Prepare for the Scoping Session
Perform a Risk Assessment
Establish Performance Objectives
Hold the Project Scoping Session
Maximizing Involvement
Why Is Involvement Important?
Sample Project Organization
Selecting the Project Team
Project Team Norms
Outline of Project Sponsor’s Kick-off Remarks
Communications Plan
Preparing to execute
Notes: These are the 11 best practices/techniques we will be covering….so let’s get started……..

## Slide 4: Team Brainstorm
You are sitting in your office when the phone rings. It’s the client – the project is a go! The initial meeting won’t be held for another two weeks since some key people are on vacation. With your team, brainstorm all of the things you need to do between now and the first meeting to get prepared.
-
Notes: Alright, let’s start this with another of our team activities……
Purpose….identify all the things a consultant would need to do once they get the “go ahead” for a project…in other words, the proposal has been accepted……good news---you won!!!!!
Directions…..first, let’s select new team leaders (select new team leaders)…..then in your teams let’s write each of your responses on an individual post-it note using your markers to write…..I will set the timer for 2 minutes……
Questions…..before I provide the final question is everybody clear?.....are there any questions that you have?......
Starting Question….OK then, think about it…you are sitting in your office and the phone rings…..(rest is on the slide).....you have 2 minutes….(when the time is up…..collect the post-its by conducing a round robin by teams and post them on a flip chart with the categories on the next slide)……..

## Slide 5: A. Prepare for the Scoping Session
Once approval to proceed is granted, detailed planning begins. A scoping session is held with key members from the client’s team to finalize all details of the project.
To prepare for the
scoping session,
consider the
following activities
(next slide).
-
Manual 8-2
Notes: [cover slide]

## Slide 6: A. Prepare for the Scoping Session
Scoping Session Preparation
Obtain a sample from a prior project of the anticipated deliverables for this project; outline the contents of the deliverables to be produced.
Prepare a draft diagram or memo summarizing your understanding of the project scope.
Update the proposal task plan as needed and add milestone dates based on the anticipated start date.
-
Manual 8-2
Notes: (consider a read around of the points on the next 4 slides focusing on the areas that were not covered in the brainstorming activity and ensure to address the following key points:
Risk assessment: the need to identify risks in the project….some will be shared with the client but all risks should be identified by the consultant….we will talk about risk assessment in more detail in a few minutes…….
The need to “load the task plan” by preparing a detailed work plan necessary to manage the project in terms of effort (budget) and schedule for all members of the project team…….
The change control process……the time to have the discussion about change control is BEFORE the first scope change arises…..by having a facilitated conversation about change control we are “getting ahead” of the inevitable change(s) that occur in almost every project….cover key reasons for change including items like unknowns with examples such as…..our scope was predicated on a conversion of 1,200 accounts and when we completed our detail design we identified 8,000 accounts AND/OR we planned our conversion prior to the acquisition of company a which added transaction volume and 4 new locations including foreign currency requirements…..as well as others identified by participants……..(reinforce the key points made earlier regarding trust, communication styles and relationship management that all can be a part of making change control conversations harder or easier……which would we prefer?......as well as points like bad news early is good news…..you have more time to deal with the news……)
Project initiation memo and kickoff meeting can be everything from a formal presentation (e.g. prime contractor and subs) to a “thanks for being on this project”……..

## Slide 7: A. Prepare for the Scoping Session
Perform a risk assessment; identify specific items to discuss with the project sponsor.
Determine your suggestion for the size of the project team based on the task plan; identify any client workers you feel are critical to the project’s success; identify the need for subject matter experts.
Develop a preliminary detailed work plan by estimating hours and completion dates for the task plan.
-
Manual 8-2
Notes: [Apply a read-around and lead the discussion.]

## Slide 8: A. Prepare for the Scoping Session
Determine the need for an executive steering committee; develop a recommended project organization chart showing reporting relationships.
Consider drafting performance objectives for the project.
Outline a plan for maintaining active communication throughout all levels of the project organization for the duration of the project.
-
Manual 8-3
Notes: [Apply a read-around and lead the discussion.]

## Slide 9: A. Prepare for the Scoping Session
Outline a plan for reviewing, approving, and accepting changes to the project plan, scope, etc.
Develop a preliminary agenda for the project orientation session.
Obtain a sample project initiation memo.
Develop a list of project logistics that need to be reviewed; be sure to include on-site work space, interview scheduling, documentation storage, and project hours.
-
Manual 8-3
Notes: [Apply a read-around and lead the discussion.]

## Slide 10: B. Perform a Risk Assessment
The purpose of a risk assessment is to identify areas of potential risk in a project in order that risk reduction strategies can be identified and implemented.
Consider assessing risk on two dimensions:
  Risk characteristics associated with an area (Favorable-Moderate-Unfavorable)
  Probability that risk characteristics will negatively impact the project (Low-Medium-High)
We recommend developing risk reduction strategies for any item receiving a high rating or a medium rating with unfavorable risk characteristics.
-
Manual 8-4
Notes: There is an old adage in project management…..maybe a good philosophy in life……and that is, “hope for the best and plan for the worst” ….as consultants we often learn that lesson by overlooking risks by hoping they will not occur, and hope is not a strategy……let’s look at the key to managing risks on our projects….
(review the slide…..reinforcing the key points about by identifying all potential risks, we can document ways to control/manage those risks with risk reduction/mitigation strategies……facilitate a discussion of experiences participants have had as either a consultant or a client regarding risks......both bad ---e.g. risks that were overlooked and then occurred --- and good---e.g. how it made a client more relieved that the consultant had their “arms around the project” and enhanced the confidence in the consultant)

## Slide 11: B. Perform a Risk Assessment
 | Characteristics Favorable Moderate Unfavorable | Probability Low Medium High | Reason for Rating
I. Project Size Number of people-hours |  |  | 
II. Management Support Understanding of project Involvement in project |  |  | 
III. Project Management Experience in subject area Experience in solution process Experience in project management |  |  | 
Manual 8-5
Notes: On the next 2 slides are a nice format or template that can be used to document and present risks to the project team and the client…..let’s look at each of the columns first…..
Characteristics…..is the risk favorable or unfavorable….can someone share an example…(name)…thanks…..
Probability…..this is the likelihood that the risk will occur……clearly we will focus our attention on those unfavorable risks that are more likely to occur….
Reason…..the “why” for that risk….for example in the experience row, if you were implementing your first SaaS or cloud system that risk might be medium or high vs. if you had implemented several SaaS or cloud systems in the past…..
Risk Reduction Strategy…..the steps you are or will be taking to reduce the impact and/or probability of that risk….this could include how you will monitor that risk with contingency plans associated with that risk……
How about the rows?…..(facilitate a discussion with participants…..some points to consider:)
Project size….larger projects typically have higher risks…especially if you have not managed larger projects….contacts with sub-contractors adds a level of complexity and, therefore, risk as well
Management support……is management on board?....what consensus exists between IT and the functional areas around system projects ….e.g. SFDC with sales, SAP with manufacturing, etc.
Experience…..as a consultant is this a project you have done in the past (Oracle or SAP install)?.....is it a process or project type you are familiar with…..

## Slide 12: B. Perform a Risk Assessment
 | Characteristics Favorable Moderate Unfavorable | Probability Low Medium High | Reason for Rating
I. Project Size Number of people-hours |  |  | 
II. Management Support Understanding of project Involvement in project |  |  | 
III. Project Management Experience in subject area Experience in solution process Experience in project management |  |  | 
Manual 8-5
Notes: Project team……how experienced is the project team….with the industry, the functional area, the process…..etc.
Planning…..how much prior planning has been completed….do the estimates have a sound basis……was the design phase thorough…….
Constraints…..have you identified constraints…..what effect will these constraints have on the project……regulatory, legal, resource, budgetary……
Technical.....is this technology well understood in general….by the members of the project…..will there be any 1sts with technical areas and/or by project team members…….)

## Slide 13: B. Perform a Risk Assessment
 | Characteristics Favorable Moderate Unfavorable | Probability Low Medium High | Reason for Rating
IV. Project Team Experience teaming together |  |  | 
V. Planning Well-defined scope Detail in work plan |  |  | 
VI. Constraints Sufficient time Sufficient human resources Sufficient funding |  |  | 
Risk Reduction Strategies |  |  | 
Manual 8-5

## Slide 14: C. Establish Performance Objectives
Avoid the expectations gap at all costs!
-
Manual 8-6
Reality
EXPECTATIONS
GAP
Expectation
OBJECTIVES
TIME
Notes: How successful will you be if you deliver your project for the client….it is on schedule and under budget…..you sit down to have your wrap-up meeting with the project sponsor and the first thing you hear about is …..well, we really wanted to have more of our people trained so that the transition moving forward would be smoother….and I really had planned on ……….guess what…..you have just been introduced to our “friend”….the Expectation Gap……
What would have happened if the client’s expectation was below reality? You would have moved from “zero” to “hero”! And, notice, reality didn’t change – just the client’s expectation.
Wow, the Expectation Gap,…..something that occurs on almost every project in some manner….sometimes it is a small gap and sometimes that gap can be large…….as the graph depicts, at project kickoff – or time 0 --- there is a large expectation gap….and that is certainly natural…..as you look at this graph I would like you to think about what it says to you….how the reality line and the expectation line move over time……..(green) team tell us what this graph say to you in terms of your role as a consultant……(go from team to team and facilitate the discussion….key points to discuss may include:
Can reality exceed expectations….what is the good (we have a client happy) and the bad (the client might think, wow could I have received what I wanted for less $$$$)
Does the expectation line always exist as a straight line or might it vary as well…….(as we do well, especially early in a project, we have to manage those expectations as well or they may become elevated)………

## Slide 15: C. Establish Performance Objectives
Strategies for Avoiding the Expectations Gap
____________________________________
____________________________________
____________________________________
____________________________________
____________________________________
-
Manual 8-7
Notes: Let’s take 2 minutes now to think about the engagements you are on now….or those engagements you have been or will be on in the near future……think about the client…..the expectation and that Expectation Gap……what are some of the strategies you can use to avoid or manage the Expectation Gap……
(at the end of the 2 minutes…..ask for a volunteer or 2 to share there strategies…..)
A really key point or theme we have found that facilitative consultants use on their projects is asking the project sponsor, the project team members the functional leaders in the client organization what they expect from the project….the results…the milestones….how they want to be involved…..how they prefer to be informed….what the communication vehicles and channels will be for the project…….remember the faintest of ink is better than the longest of memories….so document these…in some situations get sign off….periodically review them and adjust them as necessary……use STRATEGIES to avoid the Expectation Gap………

## Slide 16: C. Establish Performance Objectives
Manual 8-8
The Importance of Keeping Score
The weatherman example
Establishing performance
objectives
Tracking performance
against objectives
Reporting performance
-
Notes: Think about the importance of keeping score….how many of you have been to a high school or college football game…(raise your hand)….me, too….well can you imagine attending a Friday night high school game and the teams are marching up and down the field….people are cheering for their team….BUT there is no scoreboard…..how would that make you feel…….not very much fun….probably would not attend another one…..
How about our friend the weatherman….how many of you watch the weather on TV? (raise your hand)….how many of you trust the weather report that the weather reporter give us?....(nod your head no)……very few of us……don’t we all hear comments like…”oh the weather forecaster….they are never right, I don’t know why they report it anyway”…or words to that effect……..
Would it surprise you to learn that they weather forecast is correct almost 90% of the time on the average?...surprise you…..well, just like our football game example, in the absence of ‘keeping score’ people will rely on ‘folk lore’ or making things up….and, our tendency is to focus on the negative not the positive…in other words, our human nature would tend to look at when things were wrong vs. when they were right……so, if I were Al Roker and I had a batting average of .900 or close to that, when I was providing my forecast, rather than the time on the lower right of the screen, I would present the % of time my forecast was correct….wouldn’t that help the perception of inaccurate forecasts…….
What does that mean to us as consultants?......we must establish performance objectives and then track performance against those objectives and report that performance towards achieving those objectives……

## Slide 17: C. Establish Performance Objectives
Sample Performance Objectives
Reduce average time to produce a master schedule by 50% within the first year of use. (Current average is six weeks.)
Reduce student schedule conflicts by 60%. (Currently, 250 students are unable to get classes they request.)
Complete implementation and training prior to March 30 to permit use in spring scheduling.
-
Manual 8-9
Notes: Let’s take a look at some examples of performance objectives for a handful of projects……we like to use 3 categories of performance objectives and I would like to ask each of our teams to see what they can see as some of the categories of performance objectives included on the examples on this slide….let’s select a new team leader and I will give you 3 minutes in your teams to identify the broad categories of performance objectives you can identify from these examples……(start the clock….when time is up facilitate a discussion by using a round robin by teams with each team identifying the categories of performance objectives their team identified)……….

## Slide 18: C. Establish Performance Objectives
What are the three types of performance objectives?
P:
B:
S:
-
Manual 8-9
Notes: Nice job folks…..let’s look at 3 types of performance objectives…we refer to them as PBS:
Project/Process measures: milestones related to the project itself or how it is run
Business Outcomes: the impact on the business; results that are achieved as a result of the project
Satisfaction: the satisfaction of the stakeholders from the project or project outcomes

## Slide 19: C. Establish Performance Objectives
Performance objectives must be SMART.
S:
M:
A:
R:
T:
Manual 8-9
Notes: Remember objectives need to be SMART….in other words they should be:
Specific
Measureable
Achievable
Relevant
Time-bound…..otherwise whenever = never

## Slide 20: C. Establish Performance Objectives
Sample Performance Objectives
If you were working with the sponsor to undertake improvements in the hiring process, what might be appropriate performance objectives?
1.
2.
3.
4.
5.
-
Manual 8-10
Notes: Let’s take 3 minutes and work in teams to identify appropriate performance objectives for the project from the exercise. (Alternatively, you can use the following.)
Let’s take 3 minutes and ask each of you to think about the project you are currently working on….or one you will be tacking in the near future or one that you have completed in the not to distant past…..think about the areas where performance objectives might have been applied in that project the key areas of impact….or the stakeholder satisfaction…..or the project/process areas that might have been measured…..take those 3 minutes to write a few performance objectives that might have been applicable in that project…..(set the clock…when the time is up, ask for volunteers to share their performance objectives…..probe for…”what type of objective was that?”…..”great…does that objective pass the SMART test?’’……………………….

## Slide 21: D. Hold the Project Scoping Session
The scoping session ensures that the project starts with a clear and agreed upon plan for execution. Meet with key members of the client organization to cover key issues, including the following:
Scoping Session Checklist
Confirm the outline of the
deliverables. (Start with the
end in mind!)
Identify the start date and
target date for completion.
-
Manual 8-11
Notes: One of the key components of any project is the scoping session typically held after the project has been awarded (for external consultants) or given the “go” sign (for internal consultants)…..often, this is an informal meeting and, on occasion, this is a more formal meeting with the project team, the project sponsor and even the steering committee……let’s do a brief read-around of the key steps in the scoping session and discuss those where you may have some questions or experiences to share…..(facilitate the conversation)…..
(NOTE: one of the points to address here is the change control process….) often, consultants are accused of “scope creep” because a project took longer or was more costly than the original bid or estimate….experience tells us that this is often the result of not having a clear way to identify changes and clearly articulate those that are outside the original project scope or the results of new information in conflict with original information (e.g. when the project began there were six regions and the company expanded to eight; there was an acquisition and the acquired company is now included as a part of this project)…once again, this in another area where “the faintest of ink is better than the longest of memory”……document the change control process and explain the WII-FM to the client to help avoid this Expectation Gap.

## Slide 22: D. Hold the Project Scoping Session
Confirm the project scope.
Confirm the task plan and milestones.
Select appropriate people for the project team and those people to serve as subject matter experts.
Complete the work plan by assigning project team members to tasks and establishing due dates. (Consider making only high-level assignments during the scoping session. Save the detailed work for after the session.)
-
Manual 8-11
Notes: [Apply a read-around and lead the discussion.]

## Slide 23: D. Hold the Project Scoping Session
Establish a project organization chart and define the reporting relationships (include the steering committee and project management).
Discuss performance objectives.
Establish the communications plan (updates, issue notifications, feedback).
Establish the change control plan (approvals for changes, change limitations).
-
Manual 8-11
Notes: [Apply a read-around and lead the discussion.]

## Slide 24: D. Hold the Project Scoping Session
Schedule the project orientation session, develop the agenda, assign responsibilities, and determine appropriate attendance.
Discuss distribution of a project initiation, memo; show sample.
Review project logistics including work space, interview scheduling, documentation storage and project hours.
-
Manual 8-12
Notes: [Apply a read-around and lead the discussion.]

## Slide 25
Maximizing involvement
Notes: So, let’s jump into Phase 2, Preparing to Execute……

## Slide 26: E. Maximizing Involvement
One Way
A car manufacturer brings customers in for a focus group and listens to what they want in a car. The manufacturer designs and builds the car, has members of the focus group test it, makes adjustments based on their input, and then, rolls the car out for purchase through television advertising. They hope enough people come into their dealerships to buy the car.
-
Manual 8-13
Notes: A key to the facilitative consultant is the efforts made to involve the client…..let’s take a look at 2 different approaches that might be taken by a car manufacturer…….(name), can you read One Way……thanks, OK folks in this first way is there involvement or is their input?......(discuss and the conclusion here is the community is providing input)……great, (name)

## Slide 27: E. Maximizing Involvement
A Different Way
What if… ? A car manufacturer goes to a small town of, say, 10,000 people. The manufacturer convenes a town hall meeting to explain the program and select delegates. The delegates become part of a team that works half-time with the manufacturer on designing a car specifically for the community. The delegates constantly report progress back to the rest of the town.
-
Manual 8-13
Notes: How about A Different Way…can you read that one for us?......thanks, and is this approach can we all agree this is involvement (raise your hand)…..yes, involvement by the community…..and isn’t there a greater likelihood that the 2nd case will result in a much higher likelihood of success….input VS. involvement…a KEY difference…..

## Slide 28: E. Maximizing Involvement
When it’s time to roll out the cars, the delegates hold briefings and go door-to-door telling people about this car which they themselves worked together with the manufacturer to build.
How much better will the car manufacturer do in that community in terms of car sales?
WHY?
-
Manual 8-13
ED = RD x CD
Notes: In Robert Zawacki’s book, Transforming the Mature Information Technology Organization, he identified an equation to express the importance of involvement over input….his equation was….ED = RD x CD……..(have equation on a flip chart)……
Can anyone guess what this equation represents….let me share with you that every D stands for Decision……(facilitate the conversation)……that’s right what this equation says is an Effective Decision = Right Decision X Commitment to the Decision…..in other words are we better off with a 100% Right Decision with little to no commitment, say 10%......or an 80-90% Right Decision and 80-90% Commitment……that makes it very clear…doesn’t it……

## Slide 29: F. Why Is Involvement Important?
-
Manual 8-14
USER
VIEW
SYSTEMS
VIEW
Action
Commitment
Buy-in
Appropriate
System
Suitable
Design
Clear
Objectives
& Scope
DESIRED RESULTS
INVOLVEMENT
Notes: Our earlier automobile example was about User involvement…it leads to commitment, action and a desired outcome/results…..from a systems perspective, involvement is equally important…..it leads to clear project objectives, an understanding of scope, the right design to address a problem and an appropriate system solution to achieve the desired business results……..

## Slide 30: F. Why Is Involvement Important?
A facilitative consultant works WITH the client - not FOR the client - by including client personnel in the gathering/analysis of information and in developing recommendations.
Manual 8-14
Notes: Facilitative consultants look to work with the client – not simply for the client….this allows buy-in to become an integrated part of the consulting process…

## Slide 31: Building Commitment
In the types of projects in which you are involved, what are some ways you might build commitment while building the solution?
Manual 8-15
Notes: Let’s take another 2 minutes and ask you to think about the projects you have been on or will be working on…think about the things you can do…the people you can include….anything you and your project team can do to build commitment on that project…..(set time and facilitate the discussion after the time is out with those that would like to share their ideas……)……

## Slide 32: G. Sample Project Organization
-
Manual 8-16
Steering Committee
Project
Sponsor
Core Team
Information
Systems
Resources
Project
Leader
Subject
Matter
Experts
Notes: While there are many possible project organizations, this slide is a typical overall structure of a project…..(red) team who might be on the Steering Committee (facilitate the slide with series of questions for key areas to look at)……
(NOTES:
Steering Committee: often times Project Sponsor, senior management of important business initiatives, Project Lead/Manager, etc.)
Project Lead: often called the Project Manager….at times shared with inside PM and outside (external) consultant and the importance of communications and trust for those situations
Difference between the Core Team and the SMEs and IS Resources….get as much full time participation for the Core Team Members…for the project duration……SMEs and IS Resources may be part time for specific needs/requirements or to fulfill very specific project needs for key spots in a project…..

## Slide 33: H. Selecting the Project Team
In many projects, the quality of the results can be directly attributed to the selection of the project team members.
Responsibilities
Serve half to full-time on the project
Provide reliable information on the business area
Offer ideas and new approaches
Assess the impact of ideas on the business area
Be flexible and contribute to the team effort
-
Manual 8-17
Notes: So, let me ask the (green) team, how do you go about selecting members for your project team……(blue) team, anything to add….(facilitate the discussion and cover the key points from the next 2 slides)……….

## Slide 34: H. Selecting the Project Team
Selection (three to seven members)
As a group, should fully understand the major activities in the business area
Should be “movers and shakers” – recognized as leaders by their peers
As a group, should represent managers, supervisors, and “doers” and cover all DISC styles
Should be the people you can’t do without
-
Manual 8-17
Notes: There are some key criteria to consider in selecting members of a project team….let’s look at some of these [facilitate the discussion]

## Slide 35: I. Project Team Norms
A positive project attitude by all participants can help maintain a constructive atmosphere throughout the project. Consider adopting project team norms such as the following:
Let’s celebrate all successes.
Talk up the project and your
teammates’ strengths.
Don’t be afraid to ask for help.
Notify the project manager early if a deadline may not be met. (Missing a date without prior notification of the possibility is taboo!)
-
Manual 8-18
Notes: Team norms help to codify how the project team is going to operate together as a team…..LSI offers assistance in areas including Team Activation and Team Building to help make teams more effective…..(facilitate the discussion around key points on the next 2 slides)…….

## Slide 36: I. Project Team Norms
Arrive at least five minutes early for all team meetings, so we can start and end on time.
We don’t air our dirty linen outside the team.
If you have a problem with a project team member, take it to that person first BEFORE discussing it with others.
If a problem cannot be resolved between team members, the team members, together, should bring the issue to the project manager.
-
Manual 8-18

## Slide 37: J. Outline of Project Sponsor’s Kick-off Remarks
I
K
C
K
O
O
F
F
Empower
You were selected to be a part of this because (management, members) believe you have the experience and the vision to create recommendations that will make a difference. I want to encourage you to be creative, think outside the box, and not be constrained by the way things are done today.
Manual 8-20
Notes: Remember to address why these participants were selected and what “authority” they have been given…..

## Slide 38: J. Outline of Project Sponsor’s Kick-off Remarks
We have asked Leadership Strategies to help us on this. Leadership Strategies is in the business of providing organizations like ours with professional facilitators to help pull out their best ideas to solve their toughest problems. Our facilitator for today is… Let me tell you a little about (him/her)…
Manual 8-20
Notes: Here is a sample for a Project Sponsor’s Kick-off Remarks….

## Slide 39: K. Communication Plan
-
Audience | Information Needs | Vehicle | Who | When
Manual 8-21
Notes: How many of you have used a formal Communications Plan for one of your projects…..(name), share with us what that looked like and how that worked……great….let’s review this framework:
Audience: includes Project Steering Committee, Sponsor, Team Leads, End Users, etc.
Info Needs: status summary, project activities and progress, issues, resolutions, etc.
Vehicle: status reports, Web site/network, newsletter, executive summary

## Slide 40: MODULE REVIEW PREPARING TO EXECUTE

## Slide 41: Review
Project team
Objectives
Methodology
Risks
Project communication
Logistics
What are key categories/areas to consider in preparing for the scoping session?
-

## Slide 42: Review
Ground rules
Establish a definition of “consensus”
Take consensus checks
What are the three ways to generate a consensus-focused process?
-

## Slide 43: Review
Likelihood
Impact
What are the two key characteristics in evaluating risk?
-

## Slide 44: Review
Description of the risk
Impact of the risk (should it occur)
Timing factors (when will/might it occur?)
Risk mitigation strategies
Resources if mitigation strategies are needed
Monitoring plan – contingency plan(s)
What are the key areas to address in preparing or reviewing a risk mitigation strategy?
-

## Slide 45: Review
Status meetings
Status reports
Informal communications
What are at least three ways to manage the expectation gap?
-

## Slide 46: Review
In the absence of keeping score, people are “making up their own score,” and they may not align.
What is the importance of keeping score?
-

## Slide 47: Review
Project/process objectives
Business outcome objectives
Satisfaction objectives
What are the three types of performance objectives?
-

## Slide 48: Review
An Effective Decision is equal to
The Right Decision TIMES
The Commitment to the Decision
It is about working with the client to gain buy-in throughout the project effort
What does the equation ED = RD x CD mean?
-

## Slide 49: The Facilitative Consultant
Prepare for the Scoping Session
Perform a Risk Assessment
Establish Performance Objectives
Hold the Project Scoping Session
Maximizing Involvement
Why Is Involvement Important?
Sample Project Organization
Selecting the Project Team
Project Team Norms
Outline of Project Sponsor’s Kick-off Remarks
Communications Plan
Preparing to execute
49
Notes: Are there any questions or comments on Preparing to Execute? [facilitate the discussion]

## Slide 50: Review
Square: something that squared with what you already do or know
Circle: something that completed some circle of knowledge for you
Angle: a new angle or spin on something you have not thought of or considered
Delta: “No way, no how… Not gonna do.”
Notes: [a good review format for the end of day]

## Slide 51: Questions?
etraining@leadstrat.com
800.824.2850
Or, submit your questions for open discussion
on the Linked-In “Leadership Strategies
Facilitation & Leadership Community” Group
Join us on Facebook at
www.Facebook.com/Leadstrat
and Twitter @Leadstrat
Notes: [THIS SLIDE MAY OR MAY NOT BE INCLUDED ] We fundamentally believe facilitation is a skill that applies in a multitude of situations. We also are confident that in our quest to “share the power of facilitation with the world” that connecting via social media is a way for all of us to collectively share our successes, our challenges and our facilitation work. To “facilitate” that process, we want to ensure you are aware of how we can all stay connected using social media.
How many of you have found the skills in the class helpful? [raise your hand] I know that one of the things I did after attending was share what I learned with many of my colleagues. Have some of you already thought about that? [nod your head]
Then ,one request we would like to make of you is “like” us on Facebook. That will allow us to share tips with you periodically and allow all of us to “share the power” I have been referring to. Any questions? [facilitate the discussion]